## Cover
APEX MANAGED SERVICES LTD — ISMS INTERNAL AUDIT GUIDE
ISO/IEC 27001:2022 — Full ISMS Audit Fieldwork Workbook
AUD-2026-001 ¦ Audit Period: Q3 2026 ¦ Auditor Reference Workbook ¦ INTERNAL
Organisation | Apex Managed Services Ltd
Audit Reference | AUD-2026-001
Standard | ISO/IEC 27001:2022 (all Clauses 4–10 and Annex A Controls)
Scope | Full ISMS — per ISMS-SCO-001
Planned Fieldwork | 27–28 July 2026 (two-day programme)
Auditor | [Name] — ISO 27001:2022 Internal Auditor — [Cert No.] — see ISMS-TRN-REC Sheet 7
ISM Contact | [ISM Name] — [email] — [mobile]
Document Classification | INTERNAL
Instructions | Use this workbook as your primary fieldwork tool. For each audit item: select a finding grade in the 'Finding' column, record your notes in the 'Auditor Notes' column, and reference evidence in the 'Evidence Reviewed' column. The Findings Tracker sheet auto-counts grades.
FINDING GRADE LEGEND
C — Conformity | No nonconformity. Requirement is met. Evidence reviewed and found satisfactory.
MNC — Minor NC | A single lapse or isolated failure. Does not immediately compromise the ISMS or certification. Corrective action required within agreed timescale.
MaNC — Major NC | A systematic failure or complete absence of a required element. Directly threatens ISMS effectiveness or conformity with the standard. Corrective action required before certification/surveillance can proceed.
OFI — Opportunity for Improvement | Not a nonconformity. Observation of an area where the organisation could enhance its ISMS beyond minimum requirements.
N/A — Not Applicable | Control is excluded from scope with documented justification, or clause does not apply to this organisation's context.
NYA — Not Yet Audited | Item has not yet been assessed in this audit cycle.

## Clause Audit (4-10)
ISMS-INTERNAL AUDIT GUIDE — CLAUSE AUDIT (ISO 27001:2022 Clauses 4–10) ¦ AUD-2026-001 ¦ Apex Managed Services Ltd ¦ INTERNAL
Enter finding in column F: C (Conformity) ¦ MNC (Minor NC) ¦ MaNC (Major NC) ¦ OFI (Opportunity for Improvement) ¦ N/A ¦ NYA
IMPORTANT: Document the evidence you reviewed in column H — cite document name, version, and date. Verbal-only evidence is not sufficient for ISO 27001 findings.
Ref | Requirement | Audit Questions | Evidence to Request | ISMS Documents | Finding | Auditor Notes / Observations | Evidence Reviewed (cite doc + version/date)
4.1 | Understanding the organisation and its context | • Has the organisation identified relevant external issues (legal, regulatory, technology, competitive, geopolitical) that affect ISMS objectives? • Has the organisation identified relevant internal issues (capability, culture, governance, technology, people) that affect the ISMS? • Is the context formally documented and reviewed at least annually? • Does the context feed into risk assessment and ISMS design? | • ISMS-CTX-001 context document • Minutes showing context review occurred • Evidence of context feeding risk register | ISMS-CTX-001 | NYA
4.2 | Understanding the needs and expectations of interested parties | • Has the organisation identified all relevant interested parties (clients, regulators, CB, staff, suppliers)? • Has it documented what requirements each interested party has that are relevant to the ISMS? • Are those requirements monitored for change at regular intervals? • Do client contractual security requirements appear in the ISMS scope and risk register? | • Interested party register (ISMS-CTX-001) • Sample client contracts showing security requirements • Evidence requirements are kept current | ISMS-CTX-001 | NYA
4.3 | Determining the scope of the ISMS | • Is the scope statement documented and available? • Does the scope define the boundaries and applicability clearly — including services, people, systems, and locations? • Are exclusions from scope documented with justification? • Has the scope been communicated to the certification body? • Is the scope reviewed when organisational or operational changes occur? | • ISMS-SCO-001 scope statement • CB certification scope statement • Scope review evidence | ISMS-SCO-001 | NYA
4.4 | ISMS and its processes | • Is there evidence the ISMS is systematically managed as a set of interacting processes? • Are process inputs, outputs, owners, and performance criteria defined? • Does the ISMS operational content (ISMS-OPS-001) reflect actual operating practice? | • ISMS-OPS-001 • Process map or process reference in ISMS-CTX-001 • Evidence processes are operating | ISMS-OPS-001, ISMS-CTX-001 | NYA
5.1 | Leadership and commitment | • Has top management (MD) demonstrated active commitment to the ISMS — not just nominal sign-off? • Has the MD signed the IS Policy? • Has the MD participated in management reviews (signed minutes)? • Are ISMS roles and responsibilities assigned — documented in ISMS-LDR-001? • Is there evidence of MD communicating the importance of IS to personnel? | • Signed ISMS-POL-001 (MD signature) • Management review minutes signed by MD • ISMS-LDR-001 role assignments | ISMS-LDR-001, ISMS-POL-001, ISMS-MR-001 | NYA
5.2 | Information security policy | • Does the IS policy include a commitment to satisfying applicable requirements? • Does it include a commitment to continual improvement of the ISMS? • Is it appropriate to the organisation's purpose? • Has it been communicated to all personnel? (Policy acknowledgement records?) • Is it available to interested parties? (ISMS-POL-001-SUM) | • ISMS-POL-001 (current version, MD signed) • ISMS-POL-001-SUM (public summary) • Policy acknowledgements in ISMS-TRN-REC Sheet 5 — KPI-025 | ISMS-POL-001, ISMS-POL-001-SUM, ISMS-TRN-REC | NYA
5.3 | Roles, responsibilities and authorities | • Are IS roles and responsibilities assigned and communicated? • Is there a named ISM with the authority to report ISMS performance to top management? • Are role profiles documented? • Do all personnel know their IS responsibilities? | • ISMS-LDR-001 §5 Role Assignment Register and RACI • Job descriptions or role profiles referencing IS responsibilities • Staff awareness evidence | ISMS-LDR-001 | NYA
6.1.1 | General risk approach | • Has the organisation defined an information security risk assessment process? • Is the process documented and repeatable? • Does it include criteria for accepting risks? | • ISMS-PLN-001 §2 (risk criteria and methodology) • Risk register — is it consistent with the documented methodology? | ISMS-PLN-001 | NYA
6.1.2 | Information security risk assessment | • Has a risk assessment been performed and documented? • Does it identify risks associated with the loss of confidentiality, integrity and availability? • Are risk owners assigned to each risk? • Have likelihood and impact been assessed against documented criteria? • Is the risk assessment dated — within the last 12 months? | • ISMS-PLN-001 risk register (all 15 risks ISK-001 to ISK-015) • Evidence of risk owner sign-off • Date of most recent formal risk assessment | ISMS-PLN-001 | NYA
6.1.3 | Information security risk treatment | • Has a risk treatment plan been produced for all assessed risks? • Is the treatment option (accept, avoid, transfer, treat) documented for each risk? • Does the SoA derive from the risk treatment decisions? • Has the MD accepted residual risks that remain at High? • Is the SoA complete — all 93 controls assessed? | • ISMS-SoA-001 (all 93 controls, 87 included, 6 excluded with justification) • ISMS-PLN-001 §4 treatment plan • MD signature on risk acceptance for ISK-001 High residual | ISMS-SoA-001, ISMS-PLN-001 | NYA
6.2 | Information security objectives | • Are IS objectives documented? • Are they measurable — with KPI references and targets? • Are they monitored? (ISMS-MR-002 KPI tracking) • Are they communicated to relevant personnel? (ISMS-OBJ-001 distributed?) • Are they consistent with the IS policy? • Do objectives cover: what, resources, who, when, and how evaluated? (Clause 6.2(a)–(g)) | • ISMS-OBJ-001 — all 6 objectives with full Clause 6.2 fields • ISMS-MR-002 KPI data for OBJ-related KPIs • Evidence of communication to staff | ISMS-OBJ-001, ISMS-PLN-001, ISMS-MR-002 | NYA
6.3 | Planning of changes | • Are planned changes to the ISMS managed in a controlled way? • Is there a documented change management process? • Is there a change log with evidence of risk assessment and approval? | • ISMS-CHG-001 change management procedure • Change log entries (sample 3–5 recent changes) • Evidence of approval per the authority matrix | ISMS-CHG-001, ISMS-OPS-001 | NYA
7.1 | Resources | • Has the organisation determined and provided the resources needed for the ISMS? • Is there evidence of budget allocation for ISMS activities? • Are staff time allocations adequate for ISMS roles? | • ISMS-SPT-001 §2 resource register • Budget actuals vs. approved ISMS budget • MD confirmation of resource adequacy at management review (MRI-011) | ISMS-SPT-001, ISMS-MR-001 | NYA
7.2 | Competence | • Has the organisation determined required IS competences? • Is there evidence that personnel are competent (training, experience, qualifications)? • Are competence gaps identified and actioned? • Is effectiveness of training evaluated? | • ISMS-TRN-REC Sheet 2 (training completions) and Sheet 3 (qualifications) • ISMS-TRN-REC Sheet 6 (competence gap actions — GAP-001 to GAP-003) • Evidence of effectiveness evaluation for each gap action | ISMS-TRN-REC | NYA
7.3 | Awareness | • Are personnel aware of the IS policy and their contribution to its effectiveness? • Are they aware of the implications of not conforming to ISMS requirements? • Is there evidence of awareness training completion? (KPI-013 ≥95%) • Is there evidence of phishing simulation results? (KPI-014/015) | • ISMS-TRN-REC Sheet 2 (TRN-001 annual training completions) • ISMS-TRN-REC Sheet 4 (phishing simulation results — SIM-001 onwards) • ISMS-MR-002 KPI-013/014/015 monthly values | ISMS-TRN-REC, ISMS-HR-002, ISMS-MR-002 | NYA
7.4 | Communication | • Has the organisation determined what IS communications are needed — internal and external? • Are communication channels and responsibilities documented? | • ISMS-SPT-001 §5 (communication plan) • Evidence of IS communications to staff (e.g. policy distribution, security briefing notes) • Evidence of external communications (client security notifications, ICO liaison records) | ISMS-SPT-001 | NYA
7.5 | Documented information — management | • Is documented information controlled per the procedure? • Are documents version-controlled with approved dates? • Is access restricted by classification? • Are retention and disposal requirements defined and followed? • Is the document register current (ISMS-REG-001)? | • ISMS-DIC-001 (document control procedure) • ISMS-REG-001 document register (current version) • Sample documents — check version, date, approval, classification are all present | ISMS-DIC-001, ISMS-REG-001 | NYA
8.1 | Operational planning and control | • Are ISMS operational processes planned and controlled? • Are operational procedures documented in ISMS-OPS-001? • Is there evidence operational processes are being followed? • Are outsourced processes controlled (supplier security)? | • ISMS-OPS-001 (operational processes OPS-001 to OPS-020+) • Evidence of process outputs (e.g. access review records, patch deployment records, backup success logs) • ISMS-SUP-001 (supplier controls) | ISMS-OPS-001, ISMS-SUP-001 | NYA
8.2 | Information security risk assessment | • Has the risk assessment been updated as planned or when significant changes occur? • Is there evidence of the most recent formal risk assessment date? • Have any new risks been identified since the last assessment? | • ISMS-PLN-001 — date of most recent risk assessment • Evidence of re-assessment trigger (change, incident, or annual review) • Risk register showing current date | ISMS-PLN-001 | NYA
8.3 | Information security risk treatment | • Is the risk treatment plan being implemented? • Are treatment actions progressing against planned target dates? • Are controls from the SoA being implemented? | • ISMS-PLN-001 treatment plan — status of each treatment action • ISMS-SoA-001 implementation status column — count Implemented vs. Partially Implemented vs. Not Implemented • Evidence of specific control implementations (e.g. MFA enforcement, PAM deployment) | ISMS-PLN-001, ISMS-SoA-001 | NYA
9.1 | Monitoring, measurement, analysis and evaluation | • Are IS performance KPIs defined and being measured? • Is KPI data being collected monthly? (ISMS-MR-002 data entry) • Are measurement results being analysed and acted upon? • Can the organisation demonstrate what it monitors and when? | • ISMS-MR-002 — completed KPI data entry sheets (at least 3 months of data ideally) • ISMS-PEV-001 (performance evaluation procedure) • Evidence of analysis: management review minutes referencing KPI results | ISMS-MR-002, ISMS-PEV-001 | NYA
9.2 | Internal audit | • Has an internal audit programme been established? • Has at least one audit been conducted covering the ISMS scope? • Was the auditor independent of the area being audited? • Is there a signed independence declaration on file? • Are audit findings documented and tracked? • Has management been informed of audit results? | • ISMS-IAP-001 (audit programme — AUD-2026-001 plan) • Signed auditor independence declaration (ISMS-TRN-REC Sheet 7) • Audit report and findings • Evidence findings have been actioned (ISMS-CAR-001) | ISMS-IAP-001, ISMS-TRN-REC, ISMS-CAR-001 | NYA
9.3 | Management review | • Has management reviewed the ISMS at planned intervals? • Does the review cover all mandatory inputs (MRI-001 to MRI-015)? • Are outputs documented — including decisions and action items? • Has the MD signed the review minutes? • Were outputs actioned — can you evidence closed actions? | • ISMS-MR-001-2026 (completed signed management review minutes) • Evidence all 15 inputs were covered • Action tracker — are actions closed or progressing? • MD signature on minutes | ISMS-MR-001, ISMS-MR-002 | NYA
10.1 | Continual improvement | • Is there a process for identifying and acting on improvement opportunities? • Is the CI register being maintained? • Are CI items being progressed and closed? | • ISMS-CI-001 continual improvement register • Evidence CI items result in changes to ISMS documents or processes • Management review minutes referencing CI (MRO-001) | ISMS-CI-001, ISMS-CAR-001 | NYA
10.2 | Nonconformity and corrective action | • Are nonconformities documented when they occur? • Are corrective actions raised, with root cause analysis? • Are CARs tracked to closure? • Is there evidence of effectiveness evaluation for closed CARs? • Are there any overdue or repeat nonconformities? | • ISMS-CAR-001 — all CARs (CAR-001 to CAR-005 seeded) • Evidence of root cause analysis for each CAR • Effectiveness evaluation records for closed CARs • CA closure rate (KPI-017) | ISMS-CAR-001, ISMS-MR-002 | NYA

## Annex A Audit
ISMS-INTERNAL AUDIT GUIDE — ANNEX A CONTROL AUDIT (ISO 27001:2022 Annex A / ISO 27002:2022) ¦ AUD-2026-001 ¦ Apex Managed Services Ltd ¦ INTERNAL
Enter finding: C ¦ MNC ¦ MaNC ¦ OFI ¦ N/A (for excluded controls) ¦ NYA ¦ 6 controls excluded from scope (A.7.1–7.4, 7.6, 7.12) — marked N/A below
Cross-reference findings against ISMS-SoA-001 implementation status. A 'Partially Implemented' control in the SoA with no corrective action may indicate an MNC.
Ref | Requirement | Audit Questions | Evidence to Request | ISMS Documents | Finding | Auditor Notes / Observations | Evidence Reviewed (cite doc + version/date)
THEME 5 — ORGANISATIONAL CONTROLS (A.5.1–A.5.37 ¦ 37 controls)
A.5.1 | Policies for information security | • Is the IS policy documented, approved by management, and communicated? • Is it reviewed at planned intervals or following significant changes? | • ISMS-POL-001 signed by MD • Policy review date • Policy acknowledgements (ISMS-TRN-REC Sheet 5) | ISMS-POL-001, ISMS-TRN-REC | NYA
A.5.2 | Information security roles and responsibilities | • Are IS roles and responsibilities defined and allocated? • Is there a named ISM with sufficient authority? | • ISMS-LDR-001 §5 Role Assignment Register • RACI matrix | ISMS-LDR-001 | NYA
A.5.3 | Segregation of duties | • Are conflicting duties separated where possible? • Where not possible, is a compensating control documented (e.g. PAM session recording)? | • ISMS-LDR-001 RACI matrix • PAM session recording config evidence • Access review records showing no individual has end-to-end control of sensitive processes | ISMS-ACC-001, ISMS-LDR-001 | NYA
A.5.4 | Management responsibilities | • Does management require all personnel to apply IS per policy? • Is IS compliance a condition of employment? | • Employment contracts referencing IS obligations • ISMS-HR-001 §3.1 (contractual IS requirements) | ISMS-HR-001 | NYA
A.5.5 | Contact with authorities | • Has the organisation established contacts with relevant authorities (ICO, NCSC, Action Fraud)? • Are contact details maintained? | • ISMS-IRP-001 §15 contact directory • ICO registration number on file • NCSC and law enforcement contact in IRP | ISMS-IRP-001 | NYA
A.5.6 | Contact with special interest groups | • Is the organisation engaged with IS-relevant bodies or communities (NCSC alerts, CISA advisories, vendor security bulletins)? | • Evidence of NCSC/CISA alert subscriptions • Threat intelligence feed subscriptions • Evidence HoT monitors security advisories | ISMS-OPS-001 | NYA
A.5.7 | Threat intelligence | • Is threat intelligence collected and analysed to inform risk decisions? • Are threat intel inputs referenced in the risk register? | • Evidence of threat intel sources used in risk assessment • ISMS-PLN-001 risk register — threat descriptions • Any threat intel briefings or reports | ISMS-PLN-001 | NYA
A.5.8 | IS in project management | • Are IS requirements considered when new projects, services, or systems are introduced? • Is there a process for assessing IS impact of changes? | • ISMS-CHG-001 — IS risk assessment in change management • Evidence of IS review in recent new client onboardings or system additions | ISMS-CHG-001 | NYA
A.5.9 | Inventory of information and other associated assets | • Is an asset register maintained covering information, technology, and software assets? • Are assets classified? • Do all assets have named owners? | • ISMS-AST-001 — all three registers (IA, TA, SA) • Evidence register is current (matches Intune enrolment list) | ISMS-AST-001 | NYA
A.5.10 | Acceptable use of information and other associated assets | • Is there an Acceptable Use Policy? Has it been communicated and acknowledged? | • AUP (referenced in ISMS-HR-001 §3.1) • Evidence of AUP communication to all personnel • Joiner checklist confirming AUP acknowledged | ISMS-HR-001, ISMS-TRN-REC | NYA
A.5.11 | Return of assets | • Are organisational assets returned on departure? • Is this tracked? | • ISMS-HR-001 Leaver Checklist P2 (device retrieval items) • Asset return records for recent leavers (if any) • Intune device status for departed individuals | ISMS-HR-001, ISMS-AST-001 | NYA
A.5.12 | Classification of information | • Is information classified per a defined scheme? • Is the scheme communicated? | • ISMS-AST-001 §2 (classification scheme: CONFIDENTIAL/INTERNAL/PUBLIC) • Sample documents — check classification markings are present | ISMS-AST-001 | NYA
A.5.13 | Labelling of information | • Are information assets labelled per their classification? | • Sample ISMS documents — check headers/footers carry classification • Evidence labelling is applied consistently (e.g. CONFIDENTIAL on IRP, INTERNAL on procedures) | ISMS-AST-001, ISMS-DIC-001 | NYA
A.5.14 | Information transfer | • Are rules for information transfer defined? • Is transfer of confidential information encrypted? • Are secure transfer agreements in place with external parties? | • ISMS-OPS-001 (transfer controls) • Evidence client data is not transferred in plaintext • DPA / NDA with clients covering data transfer | ISMS-OPS-001 | NYA
A.5.15 | Access control | • Is access to information and systems restricted to authorised individuals? • Is access granted on a least-privilege basis? | • ISMS-ACC-001 (access control policy) • Entra ID group membership report • Evidence of role-based access controls | ISMS-ACC-001 | NYA
A.5.16 | Identity management | • Is each individual user account unique? No shared accounts? • Is identity verified before access is granted? | • Entra ID user list — evidence no shared accounts • Joiner checklist showing identity verification step • MFA enforcement evidence (CA-001) | ISMS-ACC-001, ISMS-HR-001 | NYA
A.5.17 | Authentication information | • Are credentials managed securely? • Are passwords not stored in plaintext? • Are credentials stored in the PAM vault? | • PAM platform credential vault evidence • Evidence passwords are not in code/config files/email • Password policy configuration in Entra ID (Password Protection enabled) | ISMS-ACC-001 | NYA
A.5.18 | Access rights | • Are access rights reviewed at regular intervals? • Are access rights revoked promptly on departure or role change? • Are privileged access rights reviewed more frequently? | • ISMS-ACC-001 §7 (access review schedule) • Evidence of quarterly privileged access review • KPI-003 leaver deprovisioning SLA records • Entra ID PIM eligible role assignment report | ISMS-ACC-001 | NYA
A.5.19 | Information security in supplier relationships | • Are IS requirements included in supplier agreements? • Is there a supplier security policy? | • ISMS-SUP-001 §2 (minimum security baseline) • Sample supplier contracts — IS clauses present? • Contractual Security Schedule template | ISMS-SUP-001 | NYA
A.5.20 | Addressing IS within supplier agreements | • Do supplier agreements include IS requirements proportionate to the risk? • Are DPAs in place where suppliers process personal data? | • ISMS-SUP-001 §5 (contractual security schedule) • Microsoft DPA (SP-001) • DPAs for other critical suppliers | ISMS-SUP-001, ISMS-RoPA-001 | NYA
A.5.21 | Managing IS in the ICT supply chain | • Are supply chain IS risks assessed? • Are sub-contractor/sub-processor controls adequate? | • ISMS-SUP-001 supplier risk register (SP-001 to SP-007) • Sub-processor register (ISMS-RoPA-001 Sheet 4) • Evidence of supply chain risk assessment | ISMS-SUP-001 | NYA
A.5.22 | Monitoring, review and change management of supplier services | • Are supplier services monitored for security performance? • Are assessments conducted at least annually? (KPI-021) | • ISMS-SUP-001 §6 (monitoring activities) • KPI-021 value in ISMS-MR-002 • Evidence of most recent supplier assessment for each critical supplier | ISMS-SUP-001, ISMS-MR-002 | NYA
A.5.23 | IS for use of cloud services | • Are cloud service IS requirements defined? • Are cloud services governed via the same supplier process? | • ISMS-SUP-001 (Microsoft Corporation SP-001 — Critical tier) • Defender for Cloud CSPM configuration • Azure Policy compliance report | ISMS-SUP-001 | NYA
A.5.24 | IS incident management — planning and preparation | • Is there a documented incident response plan? • Are IR roles and responsibilities defined? • Is there an incident classification scheme? | • ISMS-IRP-001 (IR plan, roles, P1–P5 classification, SLAs) • Evidence IR team know their roles (training records TRN-008) | ISMS-IRP-001 | NYA
A.5.25 | Assessment and decision on IS events | • Are IS events assessed and classified? • Is there a triage process? • Is there an incident log? | • ISMS-IRP-001 §3 (classification) and §5.2 (triage) • Incident log (ISMS-IRP-001 §14) — any entries? • KPI-009 (MTTD) and KPI-010 (MTTR) in ISMS-MR-002 | ISMS-IRP-001, ISMS-MR-002 | NYA
A.5.26 | Response to IS incidents | • Is there a documented response procedure? • Are playbooks available for relevant incident types? • Were recent incidents responded to per the procedure? | • ISMS-IRP-001 §5 (IR lifecycle) and Playbooks 1–5 • Any INC records in the incident log • KPI-011 (incident volume) and KPI-012 (PIR completion) | ISMS-IRP-001 | NYA
A.5.27 | Learning from IS incidents | • Are PIRs conducted after significant incidents? • Do PIR findings feed into corrective actions and improvements? | • ISMS-IRP-001 §13 (PIR template) • PIR records for any P1/P2 incidents • Evidence PIR findings fed into ISMS-CAR-001 or ISMS-CI-001 | ISMS-IRP-001, ISMS-CAR-001 | NYA
A.5.28 | Collection of evidence | • Are procedures for evidence collection and preservation documented? • Is chain of custody maintained? | • ISMS-IRP-001 §7 (evidence handling) • Evidence collection checklists • Any incident evidence preservation records | ISMS-IRP-001 | NYA
A.5.29 | IS during disruption | • Is there a BCP covering IS requirements during disruption? • Are recovery objectives defined? | • ISMS-BCP-001 (BCP and DRP) • RTO/RPO table • Key person continuity arrangements | ISMS-BCP-001 | NYA
A.5.30 | ICT readiness for business continuity | • Are ICT systems able to support business continuity requirements? • Are backup and restore procedures tested? | • ISMS-BCP-001 §4 (backup configuration and restoration test procedure) • KPI-022 (backup success rate) and KPI-023 (restoration test) in ISMS-MR-002 • Most recent restoration test report | ISMS-BCP-001, ISMS-MR-002 | NYA
A.5.31 | Legal, statutory, regulatory and contractual requirements | • Are applicable legal and regulatory IS requirements identified? • Are they incorporated into the ISMS? | • ISMS-CTX-001 (interested party register including regulators) • Evidence of UK GDPR compliance programme (RoPA, DPIA, breach log) • ICO registration | ISMS-CTX-001, ISMS-RoPA-001 | NYA
A.5.32 | Intellectual property rights | • Are software licences managed and compliant? • Is there a process to prevent use of unlicensed software? | • ISMS-AST-001 SA register (software assets with licence counts) • Evidence of licence compliance review • Intune managed app list vs. SA register | ISMS-AST-001 | NYA
A.5.33 | Protection of records | • Are IS records protected from loss, falsification, and unauthorised access? • Are retention periods defined and followed? | • ISMS-DIC-001 §6 (retention schedule) • SharePoint access controls for ISMS records • Evidence records have not been altered — version history intact | ISMS-DIC-001 | NYA
A.5.34 | Privacy and protection of personally identifiable information | • Is personal data protected in accordance with UK GDPR? • Is there a RoPA? • Are DPIAs conducted for high-risk processing? | • ISMS-RoPA-001 (complete controller and processor records) • ISMS-DPIA-001 (DPIA template + any completed DPIAs) • ICO registration • Breach log (ISMS-RoPA-001 Sheet 5) | ISMS-RoPA-001, ISMS-DPIA-001 | NYA
A.5.35 | Independent review of IS | • Is the effectiveness of the ISMS independently reviewed at planned intervals? • Is the internal audit programme being executed? | • ISMS-IAP-001 (audit programme) • Audit reports and findings • Independence declaration (ISMS-TRN-REC Sheet 7) | ISMS-IAP-001, ISMS-TRN-REC | NYA
A.5.36 | Compliance with IS policies, rules and standards | • Do managers verify compliance with IS policies and procedures? • Is non-compliance identified and acted on? | • Evidence of management monitoring (e.g. access review records, KPI review) • ISMS-CAR-001 (CARs raised for policy non-compliance) • Disciplinary records where relevant (ISMS-HR-001 §3.4) | ISMS-CAR-001, ISMS-HR-001 | NYA
A.5.37 | Documented operating procedures | • Are IS-relevant operating procedures documented? • Are they current, approved, and accessible? | • ISMS-OPS-001 (all operational processes) • Sample individual procedures — check version, approval, accessibility • ISMS-REG-001 (all procedures listed and current) | ISMS-OPS-001, ISMS-REG-001 | NYA
THEME 6 — PEOPLE CONTROLS (A.6.1–A.6.8 ¦ 8 controls)
A.6.1 | Screening | • Are background checks conducted before employment? • Are checks proportionate to role sensitivity? | • ISMS-HR-001 §2 (pre-employment screening — 7 checks) • Evidence of screening for current personnel (HR files) • Joiner checklist screening confirmation | ISMS-HR-001 | NYA
A.6.2 | Terms and conditions of employment | • Do employment contracts include IS responsibilities? • Are contractors similarly bound? | • ISMS-HR-001 §3.1 (contractual IS clauses) • Sample employment contract — IS obligations present? • Contractor agreements — IS clauses present? | ISMS-HR-001 | NYA
A.6.3 | IS awareness, education and training | • Are personnel made aware of IS threats and responsibilities? • Is training delivered and completion tracked? | • ISMS-HR-002 (awareness training procedure) • ISMS-TRN-REC Sheet 2 and Sheet 4 (training completions, phishing results) • KPI-013/014/015 in ISMS-MR-002 | ISMS-HR-002, ISMS-TRN-REC | NYA
A.6.4 | Disciplinary process | • Is there a disciplinary process for IS policy violations? • Is it applied consistently? | • ISMS-HR-001 §3.4 (disciplinary framework: Minor/Serious/Gross Misconduct) • Any disciplinary records where IS policy was violated | ISMS-HR-001 | NYA
A.6.5 | Responsibilities after termination or change of employment | • Are IS responsibilities maintained after departure? • Are NDAs enforced post-employment? | • ISMS-HR-001 §5 (post-employment obligations) • Evidence departed personnel were briefed on continuing obligations • NDA terms — do they survive termination? | ISMS-HR-001 | NYA
A.6.6 | Confidentiality or NDA agreements | • Are NDAs in place with all relevant personnel? • Are NDAs reviewed periodically? | • Signed NDAs for all current employees and contractors • Evidence NDAs are reviewed on renewal | ISMS-HR-001 | NYA
A.6.7 | Remote working | • Are remote working IS requirements defined? • Are controls applied to remote working environments? | • ISMS-OPS-001 remote working controls • Evidence of encrypted communications (TLS/VPN) • Device controls for remote endpoints (BitLocker, Intune MDM, Defender) | ISMS-OPS-001, ISMS-ACC-001 | NYA
A.6.8 | IS event reporting | • Is there a mechanism for personnel to report IS events? • Is it communicated to all personnel? | • ISMS-IRP-001 §5.1 (reporting channel and procedure) • Evidence all staff know how to report (training records TRN-004) • Any INC records in incident log | ISMS-IRP-001, ISMS-TRN-REC | NYA
THEME 7 — PHYSICAL CONTROLS (A.7.1–A.7.14 ¦ 14 controls ¦ 6 EXCLUDED — remote-first model)
A.7.1 | Physical security perimeters — EXCLUDED | • EXCLUDED FROM SCOPE: Organisation has no physical premises. • Justification: Remote-first operating model. No organisation-controlled office, data centre, or secure facility within scope. • If the organisation acquires premises, include at next SoA review. | • ISMS-SoA-001 Exclusion Justifications sheet (A.7.1) • ISMS-SCO-001 (scope confirms remote-first model) | ISMS-SoA-001, ISMS-SCO-001 | N/A | EXCLUDED — see ISMS-SoA-001 Exclusion Justifications sheet
A.7.2 | Physical entry — EXCLUDED | • EXCLUDED FROM SCOPE: No organisation-controlled premises. • Physical entry controls at client sites managed by clients. Remote working governed by A.6.7 and A.8.1 instead. | • ISMS-SoA-001 Exclusion Justifications sheet (A.7.2) | ISMS-SoA-001 | N/A | EXCLUDED — see ISMS-SoA-001 Exclusion Justifications sheet
A.7.3 | Securing offices, rooms and facilities — EXCLUDED | • EXCLUDED FROM SCOPE: No offices, rooms, or facilities within scope. | • ISMS-SoA-001 Exclusion Justifications sheet (A.7.3) | ISMS-SoA-001 | N/A | EXCLUDED — see ISMS-SoA-001 Exclusion Justifications sheet
A.7.4 | Physical security monitoring — EXCLUDED | • EXCLUDED FROM SCOPE: No premises to monitor. Logical monitoring addressed under A.8.15 and A.8.16. | • ISMS-SoA-001 Exclusion Justifications sheet (A.7.4) | ISMS-SoA-001 | N/A | EXCLUDED — see ISMS-SoA-001 Exclusion Justifications sheet
A.7.5 | Protection against physical and environmental threats | • Is the organisation dependent on cloud infrastructure for critical services? • Does the cloud provider (Microsoft) have adequate physical/environmental controls? | • Microsoft DPA / Azure compliance documentation (ISO 27001 cert) • Evidence organisation relies on Microsoft's physical controls for cloud infrastructure | ISMS-SUP-001 | NYA
A.7.6 | Working in secure areas — EXCLUDED | • EXCLUDED FROM SCOPE: No secure areas designated within organisation-controlled environments. | • ISMS-SoA-001 Exclusion Justifications sheet (A.7.6) | ISMS-SoA-001 | N/A | EXCLUDED — see ISMS-SoA-001 Exclusion Justifications sheet
A.7.7 | Clear desk and clear screen | • Are clear desk and clear screen rules applied by personnel? • Are screens locked when unattended? | • ISMS-OPS-001 (clear desk / clear screen policy reference) • Evidence of screen lock enforcement via Intune (auto-lock policy) • Awareness training covers this? | ISMS-OPS-001 | NYA
A.7.8 | Equipment siting and protection | • Is organisational equipment protected from environmental threats at home working locations? • Are devices protected from theft? | • Device encryption evidence (BitLocker — all managed laptops) • Evidence of guidance to remote workers on equipment protection | ISMS-OPS-001 | NYA
A.7.9 | Security of assets off-premises | • Are assets used off-premises (remote working, travel) protected? • Are lost/stolen device procedures defined? | • ISMS-OPS-001 (off-premises asset controls) • Remote wipe capability evidence (Intune — Wipe/Retire actions) • Device encryption (BitLocker) | ISMS-OPS-001, ISMS-AST-001 | NYA
A.7.10 | Storage media | • Is removable media use controlled? • Is data on media protected when not in use? • Is media disposed of securely? | • ISMS-OPS-001 (media controls) • Intune policy restricting USB/removable media (if configured) • Secure disposal evidence for decommissioned devices | ISMS-OPS-001 | NYA
A.7.11 | Supporting utilities | • Are critical systems protected against power failure? • For cloud infrastructure: is Microsoft's resilience adequate? | • Microsoft Azure SLA documentation • Evidence of cloud redundancy configuration (geo-redundant storage, zone-redundant services) | ISMS-BCP-001 | NYA
A.7.12 | Cabling security — EXCLUDED | • EXCLUDED FROM SCOPE: No organisation-controlled cabling. All connectivity over encrypted internet channels. | • ISMS-SoA-001 Exclusion Justifications sheet (A.7.12) | ISMS-SoA-001 | N/A | EXCLUDED — see ISMS-SoA-001 Exclusion Justifications sheet
A.7.13 | Equipment maintenance | • Is equipment maintained to ensure availability and integrity? • Is maintenance conducted by authorised personnel? | • Intune device health and compliance reports • Evidence of firmware/BIOS update management (ISMS-VUL-001 §5) • Warranty/support contract evidence for managed devices | ISMS-VUL-001 | NYA
A.7.14 | Secure disposal or re-use of equipment | • Is equipment securely wiped before disposal or re-use? • Is data destruction evidenced? | • ISMS-HR-001 Leaver Checklist P2 (Intune remote wipe) • Device disposal records • Evidence of NCSC-standard wiping (or certified destruction) | ISMS-HR-001, ISMS-AST-001 | NYA
THEME 8 — TECHNOLOGICAL CONTROLS (A.8.1–A.8.34 ¦ 34 controls)
A.8.1 | User endpoint devices | • Are all endpoint devices managed and secured? • Is there a minimum security baseline for all devices? • Are personal devices controlled if used for work? | • Intune MDM enrolment list vs. ISMS-AST-001 TA register • Intune compliance policy — what is required? • Conditional Access CA-004 (require compliant device) • BitLocker status report | ISMS-AST-001, ISMS-ACC-001 | NYA
A.8.2 | Privileged access rights | • Are privileged access rights controlled and monitored? • Is JIT access used for admin roles? • Are privileged sessions recorded? | • Entra ID PIM eligible/active role assignments • PAM platform — session recording evidence • KPI-002 (phishing-resistant MFA on privileged accounts) — 100%? • ISMS-ACC-001 §3.2 (privileged access controls) | ISMS-ACC-001 | NYA
A.8.3 | Information access restriction | • Is access to information restricted based on the access control policy? • Are need-to-know and least-privilege applied? | • Entra ID group membership report — are groups aligned to role profiles? • SharePoint permissions — CONFIDENTIAL folder access restricted? • Evidence no unnecessary access exists | ISMS-ACC-001, ISMS-AST-001 | NYA
A.8.4 | Access to source code | • Is access to source code (if applicable) restricted and controlled? | • Code repository access controls (if organisation maintains code repositories) • ISMS-AST-001 (code repos as assets?) | ISMS-AST-001 | NYA
A.8.5 | Secure authentication | • Is strong authentication enforced for access to information systems? • Is MFA enforced organisation-wide? • Are authentication events logged? | • Conditional Access CA-001 (require MFA all users) • Entra ID sign-in logs • KPI-001 (MFA coverage = 100%) in ISMS-MR-002 | ISMS-ACC-001, ISMS-MR-002 | NYA
A.8.6 | Capacity management | • Are capacity requirements monitored and managed? • Are alerts configured for resource exhaustion in Azure? | • Azure Monitor / Defender for Cloud capacity alerts • Evidence of capacity review at management review or quarterly | ISMS-OPS-001 | NYA
A.8.7 | Protection against malware | • Is malware protection deployed across all endpoints? • Is it actively monitored? • Are definitions kept current? | • Defender for Endpoint coverage report vs. Intune enrolment list • Defender security alerts dashboard • KPI-007 (scan coverage ≥99%) in ISMS-MR-002 | ISMS-VUL-001, ISMS-MR-002 | NYA
A.8.8 | Management of technical vulnerabilities | • Is vulnerability scanning performed regularly? • Are SLAs met for patching? (Critical ≤24h, High ≤7d) • Are exceptions managed and documented? | • Defender VM findings dashboard — open vulnerabilities • ISMS-VUL-001 (procedure including SLAs, exception process) • KPI-005/006/007/008 in ISMS-MR-002 • Sample exception records (if any) | ISMS-VUL-001, ISMS-MR-002 | NYA
A.8.9 | Configuration management | • Are system configurations managed and controlled? • Are hardening standards applied? • Is configuration drift detected? | • Intune configuration profile deployments • Defender for Cloud CIS benchmark compliance report • Azure Policy non-compliance report • ISMS-CHG-001 (configuration changes via change management) | ISMS-CHG-001, ISMS-VUL-001 | NYA
A.8.10 | Information deletion | • Is personal data deleted when no longer required? • Are end-of-life processes defined for data? | • Retention schedule (ISMS-DIC-001 §6) • Evidence of data deletion (e.g. leaver data deletion in ISMS-HR-001) • ISMS-RoPA-001 — retention periods defined for each processing activity | ISMS-DIC-001, ISMS-RoPA-001 | NYA
A.8.11 | Data masking | • Is sensitive data masked in non-production environments where applicable? | • Evidence of data masking in test/dev environments (if applicable) • Microsoft Purview sensitivity labels (if deployed) | ISMS-AST-001 | NYA
A.8.12 | Data leakage prevention | • Are controls in place to prevent unauthorised exfiltration of data? | • Microsoft Purview DLP policy configuration • Conditional Access — block download to unmanaged devices • Evidence of DLP alerts and responses | ISMS-OPS-001 | NYA
A.8.13 | Information backup | • Are information backups performed and tested? • Are backup procedures documented? | • ISMS-BCP-001 §4 (backup configuration and test procedure) • KPI-022 (backup success ≥99.5%) in ISMS-MR-002 • KPI-023 (restoration test 4/year) — test reports • Most recent restoration test report | ISMS-BCP-001, ISMS-MR-002 | NYA
A.8.14 | Redundancy of information processing facilities | • Are critical systems designed with redundancy? | • Azure geo-redundant storage configuration • Microsoft 365 built-in redundancy evidence • RTO targets in ISMS-BCP-001 vs. Azure SLA | ISMS-BCP-001 | NYA
A.8.15 | Logging | • Are security-relevant events logged? • Are logs protected from tampering? • Are log retention periods adequate? | • Microsoft Sentinel workspace — log retention setting (≥90 days) • Evidence Sentinel is collecting logs from key sources (Entra ID, Defender, Azure) • Log access controls — ISM and HoT only? | ISMS-OPS-001 | NYA
A.8.16 | Monitoring activities | • Are systems monitored for IS events? • Are alerts reviewed and acted upon? • Is there evidence of active monitoring? | • Sentinel incident queue — recent alerts and closure evidence • Defender portal — active investigations • KPI-009 (MTTD) and KPI-010 (MTTR) in ISMS-MR-002 | ISMS-OPS-001, ISMS-MR-002 | NYA
A.8.17 | Clock synchronisation | • Are system clocks synchronised to ensure log correlation is accurate? | • Azure NTP synchronisation configuration • Evidence endpoint clocks are synchronised (Intune/domain policy) | ISMS-OPS-001 | NYA
A.8.18 | Use of privileged utility programs | • Are utility programs that can override system controls restricted? | • Evidence of privileged tool access controls (PAM) • Intune app restriction policies • Evidence utility tool use is logged | ISMS-ACC-001 | NYA
A.8.19 | Installation of software on operational systems | • Is software installation on managed systems controlled? • Can users install unapproved software? | • Intune app control configuration (allow/block lists) • Conditional Access / Defender Application Control evidence • ISMS-VUL-001 §5 (patch and software deployment via Intune) | ISMS-VUL-001 | NYA
A.8.20 | Networks security | • Are networks segmented and protected? • Is internet-facing traffic controlled? | • Azure NSG and firewall configuration • Evidence of network segmentation in Azure • Defender for Cloud network security recommendations | ISMS-OPS-001 | NYA
A.8.21 | Security of network services | • Are network services secured? • Are service provider SLAs and security requirements defined? | • ISP/connectivity provider agreement — IS requirements? • Azure networking security configuration • ISMS-SUP-001 (network service providers assessed?) | ISMS-SUP-001 | NYA
A.8.22 | Segregation of networks | • Are development/test environments separated from production? • Are client environments isolated from each other? | • Evidence of Azure subscription/resource group isolation per client • Evidence production and non-production are separated | ISMS-OPS-001 | NYA
A.8.23 | Web filtering | • Is web access filtered to block malicious content? • Is there evidence filtering is active? | • Defender SmartScreen / web filtering configuration • Evidence of web filtering policy in Intune or Defender | ISMS-OPS-001 | NYA
A.8.24 | Use of cryptography | • Are cryptographic controls applied to protect sensitive information? • Are encryption keys managed securely? | • BitLocker encryption status for all managed devices • TLS 1.2+ enforcement evidence • Azure Key Vault for key management • Evidence client data encrypted at rest and in transit | ISMS-OPS-001, ISMS-AST-001 | NYA
A.8.25 | Secure development lifecycle | • If the organisation develops software/scripts, are security requirements included in development? | • Evidence of secure coding practices (if applicable) • Any internal tooling or scripts — security review evidence | ISMS-OPS-001 | NYA
A.8.26 | Application security requirements | • Are security requirements defined for applications used in service delivery? | • ISMS-AST-001 SA register — security controls noted per application • Evidence of security assessment for new SaaS tools | ISMS-AST-001, ISMS-CHG-001 | NYA
A.8.27 | Secure system architecture and engineering principles | • Are secure-by-design principles applied to system architecture? • Is zero-trust architecture principles applied? | • Evidence of Conditional Access zero-trust model (CA-001 to CA-008) • Defender for Cloud secure score recommendations • Architecture documentation or design decisions referencing security principles | ISMS-ACC-001 | NYA
A.8.28 | Secure coding | • Are secure coding practices followed for any developed code? | • Script/code review evidence (if internal tooling exists) • Evidence of input validation, error handling in any custom-developed tools | ISMS-OPS-001 | NYA
A.8.29 | Security testing in development and acceptance | • Is security testing performed before deploying new systems or significant changes? | • ISMS-CHG-001 (post-implementation review step) • Evidence of security testing for recent significant changes | ISMS-CHG-001 | NYA
A.8.30 | Outsourced development | • If development is outsourced, are security requirements included in contracts? | • Relevant contracts — IS requirements clause • Supplier assessment (ISMS-SUP-001) for development providers | ISMS-SUP-001 | NYA
A.8.31 | Separation of development, test and production environments | • Are development, test, and production environments separated? | • Evidence of environment separation (separate Azure subscriptions/resource groups) • Evidence production data is not used in test environments | ISMS-OPS-001 | NYA
A.8.32 | Change management | • Are changes to IS-relevant systems managed per a change management process? | • ISMS-CHG-001 (change procedure — 3 types, 7-step workflow, approval matrix) • Sample change log entries — evidence of risk assessment and approval • Emergency changes — evidence of verbal approval + written follow-up within 24h | ISMS-CHG-001 | NYA
A.8.33 | Test information | • Is test data managed and protected? • Is personal data anonymised before use in test environments? | • Evidence test environments do not contain live personal data • ISMS-RoPA-001 (does test data processing appear as processing activity?) | ISMS-RoPA-001 | NYA
A.8.34 | Protection of information systems during audit testing | • Are audit tests planned to minimise disruption to production systems? • Is audit access controlled and logged? | • ISMS-IAP-001 (audit plan — fieldwork methodology) • Evidence auditor access is read-only and logged • Audit test scope agreement | ISMS-IAP-001 | NYA

## Findings Tracker
FINDINGS TRACKER — Record all MNC, MaNC, and OFI findings here. C and N/A findings do not require a tracker entry.
MaNC: corrective action plan required before certification/surveillance can proceed. MNC: agreed timescale with auditee. OFI: no mandatory action.
| Finding Ref | Clause / Control Ref and Title | Grade | Finding Statement | Objective Evidence | Root Cause (MNC/MaNC) | Corrective Action Required | Target Close Date

## Interview Log
INTERVIEW LOG — Record all auditee interviews. Verbal evidence alone is insufficient; always request corresponding documented evidence.
| Date / Time | Auditee Name | Role | Topics Covered / Questions Asked | Key Responses / Evidence Referenced

## Document Sample Log
DOCUMENT SAMPLE LOG — Record every document reviewed during fieldwork. Log the version, date, and classification. Note any control weaknesses in Comments.
| Document / Record Name | ISMS Reference | Version Sighted | Date on Document | Classification Correct? | Auditor Comments / Control Weaknesses Noted

## Audit Summary Report
ISMS INTERNAL AUDIT SUMMARY REPORT — AUD-2026-001 ¦ Complete after fieldwork is done. This is the formal audit report for management.
| Audit Reference | AUD-2026-001
| Organisation | Apex Managed Services Ltd
| Standard | ISO/IEC 27001:2022
| Scope | Full ISMS — per ISMS-SCO-001
| Fieldwork Dates | [Date] to [Date]
| Lead Auditor | [Name] — [Qualification]
| Report Date | [Date]
| Distribution | Managing Director; Information Security Manager
FINDING SUMMARY
| Major NCs (MaNC) | [Count] — must be resolved before certification/surveillance proceeds
| Minor NCs (MNC) | [Count] — corrective action within agreed timescale
| Opportunities for Improvement (OFI) | [Count] — no mandatory action but recommended
| Conformities (C) | [Count] — requirements met, evidence reviewed
| Not Applicable (N/A) | 6 — excluded controls per SoA (A.7.1/2/3/4/6/12)
| Not Audited | [Count] — items not covered in this audit cycle (if any)
AUDIT OBJECTIVE AND SCOPE
State the objective (determine conformity with ISO 27001:2022 and ISMS-IAP-001 AUD-2026-001 plan) and confirm scope covered.
OVERALL AUDIT CONCLUSION
State overall conclusion: does the ISMS conform to the requirements of ISO/IEC 27001:2022 and the organisation's own documented requirements? Is certification recommended?
SIGNIFICANT POSITIVE OBSERVATIONS
Note areas of strong performance or good practice observed. These are not findings — they are recognition of effective implementation.
MAJOR NONCONFORMITIES (if any)
For each MaNC: state the requirement clause, the finding, and the objective evidence. State required corrective action and deadline.
MINOR NONCONFORMITIES (if any)
For each MNC: state the requirement clause, the finding, and the objective evidence. State agreed corrective action and timescale.
OPPORTUNITIES FOR IMPROVEMENT
List OFIs — areas where improvement is possible beyond minimum requirements. Non-mandatory.
AUDITOR DECLARATION
I confirm this audit was conducted in accordance with ISMS-IAP-001, the independence declaration filed in ISMS-TRN-REC Sheet 7, and ISO 19011:2018 principles. Findings represent my professional judgement based on the evidence reviewed during fieldwork. Auditor signature: ____________________________ Date: ____________________________ Report acknowledged by ISM: ____________________________ Date: ____________________________ Report acknowledged by MD: ____________________________ Date: ____________________________

## Two-Day Agenda
AUD-2026-001 — SUGGESTED TWO-DAY AUDIT AGENDA ¦ Fieldwork 27–28 July 2026 ¦ Adjust timings to actual schedule
| Time | Session / Area | Clauses / Controls | Auditees
| DAY 1 — 27 July 2026 | 1F3864
| 09:00–09:30 | Opening Meeting | Introductions. Confirm scope, objectives, agenda, logistics. Confirm independence declaration received. | MD, ISM, HoT
| 09:30–11:00 | Context, Leadership, and Planning | Clauses 4.1, 4.2, 4.3, 4.4, 5.1, 5.2, 5.3, 6.1, 6.2, 6.3. Review ISMS-CTX-001, ISMS-SCO-001, ISMS-LDR-001, ISMS-POL-001, ISMS-SoA-001, ISMS-OBJ-001, risk register. | MD, ISM
| 11:00–12:30 | Support and Performance | Clauses 7.1–7.5, 9.1, 9.3. Review ISMS-SPT-001, ISMS-TRN-REC, ISMS-MR-002, ISMS-MR-001-2026, ISMS-DIC-001. | ISM
| 12:30–13:30 | Lunch break | — | —
| 13:30–15:00 | Access Control and HR Security | A.5.15–A.5.18, A.6.1–A.6.8, A.8.2. Review ISMS-ACC-001, ISMS-HR-001, Entra ID PIM report, PAM session recording evidence, Conditional Access policies (CA-001 to CA-008). | ISM, HoT
| 15:00–16:30 | Asset Management and Vulnerability Management | A.5.9–A.5.14, A.8.1, A.8.7–A.8.9, A.8.19. Review ISMS-AST-001, ISMS-VUL-001, Defender VM findings, Intune compliance report, Secure Score (KPI-008). | HoT
| 16:30–17:00 | Day 1 Wrap — Auditor Working Time | Auditor reviews notes, updates findings in this workbook, prepares Day 2 focus. | Auditor only
| DAY 2 — 28 July 2026 | 1F3864
| 09:00–10:30 | Incident Response and BCP | A.5.24–A.5.30. Review ISMS-IRP-001 (IR plan, playbooks, contact directory, incident log), ISMS-BCP-001, backup restoration test records (KPI-022/023). | ISM, HoT
| 10:30–12:00 | Supplier Management and Data Protection | A.5.19–A.5.23, A.5.34. Review ISMS-SUP-001 (supplier register SP-001 to SP-007), ISMS-RoPA-001 (controller and processor records), ISMS-DPIA-001. | ISM
| 12:00–13:00 | Lunch break | — | —
| 13:00–14:30 | Operations, Cloud Security, Logging, Monitoring | Clauses 8.1–8.3, A.8.13–A.8.17, A.8.20–A.8.24, A.8.32. Review ISMS-OPS-001, Sentinel workspace config, Defender for Cloud CSPM, Azure Policy, ISMS-CHG-001 change log. | HoT
| 14:30–15:30 | Corrective Action and Continual Improvement | Clauses 10.1, 10.2, 9.2. Review ISMS-CAR-001 (CAR-001 to CAR-005), ISMS-CI-001, ISMS-IAP-001, auditor independence declaration. | ISM
| 15:30–16:00 | Auditor Working Time — Finalise Findings | Complete findings in workbook. Prepare Audit Summary Report draft. | Auditor only
| 16:00–17:00 | Closing Meeting | Present findings summary to MD and ISM: MaNC count, MNC count, OFI count. Agree corrective action timescales for MNCs. Sign audit report. | MD, ISM, HoT